## Product Backlog
g | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-101 | LLM concepts such as self-attention, Query-Key-Value and context | MUST HAVE | None | MARUGE SHRISH | 3- Completed
S2 | S2 | US-201 | As a researcher, I want to understand supported financial document structures so the system can process annual reports, 10-K filings, and earnings transcripts. | MUST HAVE | Document ingestion design | MARUGE SHRISH | 3- Completed
S2 | S2 | US-202 | As a researcher, I want PDFs parsed into readable text so their contents can be processed. | SHOULD HAVE | US-202 | MARUGE SHRISH | 3- Completed
S2 | S2 | US-203 | As a developer , I want to present Project and get reviewed by the Mentor | SHOULD HAVE | Review of the Sprint 2 | MARUGE SHRISH | 3- Completed
S3 | S3 | US-301 | As a researcher, I want the Red Flag Agent to identify anomalies, rising debt, falling margins, auditor qualifications, and unusual patterns. | MUST HAVE | US-204 | MARUGE SHRISH | 3- Completed
S3 | S3 | US-302 | As a researcher, I want Document, Extraction, and Red Flag Agents to run sequentially after a document upload. | MUST HAVE | US-301 | MARUGE SHRISH | 3- Completed
S3 | S3 | US303 | As a developer, I want outputs validated against seed documents for correctness and source faithfulness. | MUST HAVE | US-302 | MARUGE SHRISH | 3- Completed
S3 | S3 | US-304 | As a researcher, I want the Research Agent to answer multi-part questions using retrieved passages and strict source citations. | MUST HAVE | US-303 | MARUGE SHRISH | 3- Completed
S3 | S3 | US-305 | As a developer , I want to present Project and the working with code flow and get Reviewed by the mentor | SHOULD HAVE | Review of the Sprint 3 | MARUGE SHRISH | 3- Completed
S4 | S4 | US-401 | As a researcher, I want a complete analyst-style PDF combining Executive Summary, Key Financials, Red Flags, Company Comparison, and Outlook. | MUST HAVE | US-305 | MARUGE SHRISH | 3- Completed
S4 | S4 | US-402 | As a developer, I want end-to-end tests for citation accuracy, extraction correctness, agent collaboration, and report completeness. | MUST HAVE | US-401 | MARUGE SHRISH | 3- Completed
S4 | S4 | US-403 | As a developer, I want retrieval quality, prompts, and orchestration reliability optimized across varied financial document formats. | SHOULD HAVE | US-402 | MARUGE SHRISH | 3- Completed
S4 | S4 | US-404 | As a developer , Completed Mock interview Explaining the project from the team of 2 Agents before a final presentation | MUST HAVE | US-404 | MARUGE SHRISH | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1-4 BACKLOG
US-101 | T-101-1 | Study LLM fundamentals, embeddings, vector search, and RAG concepts | 2026-09-10 | 2026-09-11 | MARUGE SHRISH | Research | Completed
US-201 | T-201-1 | Review annual report structure | 2026-09-12 | 2026-09-12 | MARUGE SHRISH | Research | Completed
US-202 | T-201-2 | Implement PDF upload validation and text parsing | 2026-09-12 | 2026-09-17 | MARUGE SHRISH | CODING | COMPLETED
US-203 | T-203-3 | Reviewed the 2 agents given in S2 | 2026-09-18 | 2026-09-18 | MARUGE SHRISH | review | Completed
US-301 | T-301-1 | Implement anomaly and debt-trend checks | 2026-09-26 | 26-0926 | MARUGE SHRISH | CODING | COMPLTED
US-302 | T-302-2 | Sequence Document, Extraction, and Red Flag Agents | 2026-09-28 | 2026-09-28 | MARUGE SHRISH | CODING | COMPLETED
US-303 | T-303-3 | Validate extracted values against PDF evidence | 2026-09-29 | 2026-09-29 | MARUGE SHRISH | CODING | COMPLETED
US-304 | T-304-4 | Implement multi-part research retrieval and citations | 2026-10-01 | 2026-10-01 | MARUGE SHRISH | CODING | COMPLETED
US-305 | T-305-5 | REVIEWED THE 5 AGENTS OF THE PROJECT | 2026-10-07 | 2026-10-07 | MARUGE SHRISH | REVIEW | COMPLETED
US-401 | T-401-1 | Compile all agent outputs into final analyst-style PDF | 2026-10-12 | 2026-10-12 | MARUGE SHRISH | CODING | COMPLETED
US-402 | T-402-2 | Run end-to-end tests and verify report completeness | 2026-10-13 | 2026-10-13 | MARUGE SHRISH | TESTING | Completed
US-403 | T-403-3 | Tune prompts, retrieval quality, and orchestration reliability | 2026-10-14 | 2026-10-14 | MARUGE SHRISH | TESTING | COMPLETED
US-404 | T-404-4 | MOCK presentation PRESENTED 2 AGENTS OF THE PROJECT | 2026-10-16 | 2026-10-16 | MARUGE SHRISH | mock presentation | COMPLETED
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
5 | Day | Impediments | Action Taken
s1 | day1 | Needed to understand concepts of llm,lang-chain ect | Studied the concepts and give the answers to the asked questions
s2 | day1 | studied embeddings and vector databases. | Studied RAG, embeddings, ChromaDB, and multi-agent architecture documentation.
s2 | day2 | Database model relationships were unclear. | Defined ResearchSession, Document, FinancialMetric, and RedFlag models.
s2 | day3 | Frontend and backend connection required configuration. | Configured API URL, CORS, and session APIs.
s3 | day1 | Some PDFs may contain unreadable or scanned text. | Added readable-text validation and clear error handling.
s3 | day2 | Red flags can create false positives if rules are broad. | Used specific risk phrases and source-evidence requirements.
s3 | day3 | Research answers needed to remain source-grounded. | Added retrieval, citations, and fallback evidence response.
s4 | day1 | Need to validate report completeness and citations. | Created end-to-end testing checklist and source-page review.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7