## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | MARUGE SHRISH | 2026-09-10 | The initial project explanation did not clearly distinguish LLM concepts, RAG, embeddings, and agent responsibilities. | S1 | MARUGE SHRISH | Logical | Prepared a structured architecture explanation and project Q&A for US-101. | 2026-09-11 | Closed | Resolved during task T-101-1. Project concepts and agent roles were documented.
2 | MARUGE SHRISH | 2026-09-12 | The upload flow could accept non-financial or unrelated PDF documents, affecting analysis quality. | S2 | MARUGE SHRISH | Standards | Added PDF and annual-report content validation before document processing. | 2026-09-17 | Closed | Resolved under US-202 / T-201-2. The system now rejects unrelated PDFs with an error message.
3 | MARUGE SHRISH | 2026-09-15 | Some scanned or unreadable PDFs returned no usable text, causing document processing failure. | S2 | MARUGE SHRISH | Logical | Added readable-text checks and clear processing error messages. | 2026-09-17 | Closed | Resolved under US-202. Text-based annual reports are required; image-only PDFs are flagged for OCR.
4 | MARUGE SHRISH | 2026-09-18 | Extracted financial metrics did not consistently retain source-page evidence for user verification. | S2 | MARUGE SHRISH | Maintainability | Stored metric value, period, evidence text, source page, and confidence in the database. | 2026-09-22 | Closed | Resolved under US-202 / T-203-3. Extracted metrics are traceable to the annual report.
5 | MARUGE SHRISH | 2026-09-22 | The frontend did not clearly display extracted amounts, source pages, and processing outcomes. | S2 | MARUGE SHRISH | User Interface | Updated the workspace to show financial metric cards, status messages, and source-page links. | 2026-09-23 | Closed | Resolved after the Milestone 2 review. Users can view extracted values clearly.
6 | MARUGE SHRISH | 2026-09-26 | Broad red-flag matching could produce weak or unclear risk signals without enough explanation. | S3 | MARUGE SHRISH | Logical | Defined specific red-flag rules for debt, liquidity, margins, audit, revenue, and legal disclosures. | 2026-09-30 | Closed | Resolved under US-301 / T-301-1. Every flag requires a configured risk pattern.
7 | MARUGE SHRISH | 2026-10-01 | Red Flag output displayed missing or zero confidence for reports processed before the new scoring fields existed. | S3 | MARUGE SHRISH | Maintainability | Added confidence, matched-signal, and confidence-explanation fields and reprocessed documents. | 2026-10-02 | Closed | Resolved under US-303 / T-303-3. The score is stored by the backend and shown with evidence.
8 | MARUGE SHRISH | 2026-10-03 | Research answers could be too generic if retrieval evidence and source citations were not enforced. | S3 | MARUGE SHRISH | Standards | Implemented document retrieval, source excerpts, page citations, and a source-grounded fallback response. | 2026-10-06 | Closed | Resolved under US-304 / T-304-4. Research responses are tied to selected report evidence.
9 | MARUGE SHRISH | 2026-10-06 | Comparison of selected reports could fail when reports were incomplete or selected from different sessions. | S3 | MARUGE SHRISH | Logical | Added validation for completed reports, matching session IDs, and available extracted metrics. | 2026-10-07 | Closed | Resolved under US-305 / T-305-5. The Comparison Agent returns clear validation errors.
10 | MARUGE SHRISH | 2026-10-07 | Users could not easily understand the evidence behind Research Agent and Red Flag Agent outputs. | S3 | MARUGE SHRISH | User Interface | Added chat citations, retrieval steps, risk evidence cards, source-page links, and confidence explanation. | 2026-10-08 | Closed | Resolved after the Milestone 3 review. Output presentation is source-focused and readable.
11 | MARUGE SHRISH | 2026-10-12 | The initial report output did not combine all agent results into one consistent analyst-style document. | S4 | MARUGE SHRISH | Standards | Defined the Report Agent structure: Executive Summary, Key Financials, Red Flags, Company Comparison, and Outlook. | 2026-10-12 | Closed | Resolved under US-401 / T-401-1. The report structure now covers all required sections.
12 | MARUGE SHRISH | 2026-10-13 | End-to-end validation did not initially verify citations, extraction results, agent sequencing, and report completeness together. | S4 | MARUGE SHRISH | Logical | Created end-to-end test cases and checked outputs against annual-report source pages. | 2026-10-13 | Closed | Resolved under US-402 / T-402-2. Testing covers citation accuracy, extraction correctness, and agent collaboration.
13 | MARUGE SHRISH | 2026-10-14 | Retrieval quality and orchestration could vary across different annual-report formats and long documents. | S4 | MARUGE SHRISH | Maintainability | Refined chunking, retrieval selection, prompts, and error handling for varied financial document formats. | 2026-10-14 | Closed | Resolved under US-403 / T-403-3. Reliability improvements were validated during Milestone 4 testing.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others